Objective 1: To baptize 50 people in the first year and 75 in the subsequent years

|  | Strategy | Activities | Time frame Begin Date: End Date: | Responsibility | Performance indicator | Costs/inputs |
| --- | --- | --- | --- | --- | --- | --- |
| 1. | - Form 10 evangelism groups within the church of which each should realize at least one member every quarter | - Member Identified and assigned evangelism groups - Evangelistic activities conducted | 01/04/2012……… April 2012 2013- Feb | Personal Ministries Leader. | Groups formed Evangelistic Quarterly |  |
| 2. | - Conduct, at least, one health expo each year | - Booking of venue - Communications With resource persons - Logistics - Marketing of event (printing of fliers, Banner(s) | Every August each year | Health Department |  |  |
| 3. | - To train 20% of the Church membership as evangelists by 2014 | - Identification of evangelists - Organize a workshop(s) | Every in July | Publishing Leader | 20 members trained each year One workshop conducted |  |
| 4. | - To establish a company in year 2 | - Identification of location for the company | December 2013 | Elder’s Board | Company established by 2013 |  |
| 5. | - Use DVD evangelism | - Identification and verification of DVDs - Cutting of DVDs - Distribution of DVDs | April 2012 | Personal Ministries | 50 DVDs distributed Annually |  |
| 6. | - Each member to at least distribute one Voice Of Prophesy pamphlet | Sorting out of VOP pamphlets | April 2012 | Personal Ministries | 100 copies per year |  |

Objective 2: To improve systematic giving by 20% every year

|  | Strategy | Activities | Time frame Begin Date: End Date: | Responsibility | Performance indicator | Costs/inputs |
| --- | --- | --- | --- | --- | --- | --- |
| 1. | - Form 10 Stewardship visitations groups (each group to have 3 members) - Each group to visit 6 members (visit 60 members per quarter) | - Recruit more members for the formation of groups - Select group leaders - Identify which members’ cars will be used for visitations - Time table for the visitations - Notification of the church members to be visited | March 2012 March 2012 March 2012 March 2012 April 2012 | Stewardship Leader. | 10 group formulated Group Leaders List of cars to be used Time table Notices | - |
| 2. | - Offertory reading | - Create a Rota for reading offertory stories. - Reminding the Specific Readers | Weekly | Stewardship Department | Rota created and offertory read Reminders done to ensure people are reading the offertory message |  |
| 3. | - Sabbath School promotions | - Create a Rota for the promotions - Informing the promoters - Reminding the promoters | March 2012 On-going | Stewardship Department | Promotions done every Sabbath Rota created |  |
| 4. | - Conduct Bible studies on Stewardship (self reliance, Offerings and local church budget, offerings on church building, tithe of non-monetary increases, stewardship of time) | - Identify and inform the bible study facilitators - Logistics for the facilitators | February 2012 Quarterly | Stewardship Department | Bible studies conducted February, July and October |  |
| 5. | - Encourage Church members to help nonworking members find employment - To conduct encouragement campaigns at the start of every bible study and during offertory readings | - Make announcements on helping nonworking members - Introduce a corner in the church bulleting | Monthly February 2012 | Stewardship Department | One promotion done every month Announcement presented in the bulletin weekly |  |
| 6. | - Church members sign recommitment forms -Utilizing the stewardship month (get recommitments to support the church in tithes and offering) | - Printing of stewardship recommitment cards - Call for recommitments | February 2012 February 2012 | Stewardship Department | Recommitment done annually |  |
| 7. | - Open a Church school by 2014 | Subject to having a church plot | Subject to having a church plot | Education Department | Subject to having a church plot |  |

Objective 3: To raise 100 million per quarter towards Church building and to have a complete Church Structure by 2014

|  | Strategy | Activities | Time frame Begin Date: End Date: | Responsibility | Performance indicator | Costs/inputs |
| --- | --- | --- | --- | --- | --- | --- |
| 1. | - Use family targets- |  | Quarterly | Church Building Leader. | Zmk100,000m |  |
| 2. | - Tax refunds ( Education on tax refund- give 50% of the claim to church building and the rest could be used by the church members-all salaried employees should be encourage to make claims) |  | April 2012 March 2012 |  | 10 refunds per year |  |
| 3. | - Buy a brick project |  | April 2012 | Church Building Leader | Booklets printed and sold-out |  |
| 4. | - Quarterly Church promotions |  | Quarterly | Church Building Leader | Promotions done |  |
| 5. | - 1st year slab put |  | December 2012 | Church Building Leader. | Slab | ZMK 400,000m |
| 6. | - 2nd year supper slab |  | December 2013 |  | Super structure | Zmk 600,000m |
| 7. | - 3rd year internal accessories |  | December 2014 |  | Complete church | Zmk 100,000m |

Objective 4: To strengthen the spirituality of church members so as to serve God faithfully

|  | Strategy | Activities | Time frame Begin Date: End Date: | Responsibility | Performance indicator(s) | Costs/inputs |
| --- | --- | --- | --- | --- | --- | --- |
| 1. | - Organize a retreat at the beginning of every year. |  | Every January | Personal Ministries Leader | A Retreat |  |
| 2. | - Encourage attendance during weeks of prayer |  | Every week of prayer |  | Week of Prayer |  |
| 3. | - Re-introduce vespers on Fridays and Sabbaths |  |  | Personal Ministries |  |  |
| 4. | - Encourage zone meetings on Wednesday |  |  |  |  |  |
| 5. | - Involve member participation in various programmes |  |  |  |  |  |
| 6. | - Create directory of members |  | July 2012 Update in January 2013 & 2014 | Communication | Database created by July 2012 Database updated in January 2013 & January 2014 |  |
| 7. | - Visitations to nurture members |  | Begin in April 2012-2014 | Elders’s Board, Stewardship department and Deacons | 150 members visited annually |  |

Objective 5: To undertake at least 6 social corporate activities annually

|  | Strategy | Activities | Time frame Begin Date: End Date: | Responsibility | Performance indicator | Costs/inputs |
| --- | --- | --- | --- | --- | --- | --- |
| 1. | - 30 million raised towards prison, hospital and orphanage | - Prison Ministries - Hospital visitations - Orphanage | April 2012 2012 -2014 once per quarter 2012 once 2013 1st & 3rd quarter 2014 1st & 3rd quarter | AMO, Docas AY societies AMO, Dorcas, AY societies, Children’s Ministries, Adventurer, AY | Prison Visit Hospital Visits Orphanage visit | K30 million |
| 2. | Helping the needy within the Church to raise K20 million | - Identify the needy people within the church - Needy basket - Sponsorship [ School fees (4 people)] | 2012 – 2nd quarter 2013- 1st quarter 2014 – 1st quarter 2012 – 2nd quarter 2013- 1st quarter 2014 – 1st quarter 2012 -2014 once per quarter – 2012 – 2014 once per quarter | AMO, Dorcas, Women’s Ministries and Deacons | Four (4) members helped annually Four (4) members helped annually Four (4) members helped annually | K5 million per quarter |

Objective 6: To help the needy within the Church

|  | Strategy | Activities | Time frame Begin Date: End Date: | Responsibility | Performance indicator | Costs/inputs |
| --- | --- | --- | --- | --- | --- | --- |
| 1. | - Identify the needy within the Church |  |  | Deacons | - Needy identified |  |
| 2. | - Raise 20 million Kwacha every year towards the needy within the Church |  |  | Stewardship Department | - 5 million raised every quarter |  |

Objective 7: To identify and effectively use the various available professions and skills within the church to enhance our service delivery

|  | Strategy | Activities | Time frame Begin Date: End Date: | Responsibility | Performance indicator | Costs/inputs |
| --- | --- | --- | --- | --- | --- | --- |
| 1. | - Organize a workshop to identify people’s spiritual gifts. | Conduct seminar to help identify spiritual needs | 2012 – May 2013-Jan 2014- Jan | Education leader | Workshops conducted and Spiritual gifts Identified |  |
| 2. | - Create a database of members’ professions, expertise, and skill. ( This information should be used by the nominating committee) |  | 2012 –May 2013- Jan 2014- Jan | Education leader | Database Created and updated |  |

Objective 8: To train serving officers at the beginning of every year.

|  | Strategy | Activities | Time frame Begin Date: End Date: | Responsibility | Performance indicator | Costs/inputs |
| --- | --- | --- | --- | --- | --- | --- |
| 1. | - Organize a training workshop for serving officers |  | May-2012 January-2013 January-2014 | Elders board | Officers Trained |  |
| 2. |  |  |  |  |  |  |